## Project Overview
IT Project Requirements Template
Project Overview
Project Name: | Workforce Management
Project #: | <DSR019>
Date: | 2025-06-09
Description: | Workstream to enhance the accessibility, accuracy, and usability of training and competency data within ATCO.
Project Sponsor: | Cristina Jackle
TPAG Program Manager:
IAM Program Manager:
IAM Manager:
Project Manager: | Carmen Galue
Business Analyst | Anastasiia Turba
Template: May 8 2020

## Business Requirements
IT Project Requirements Template
Business Requirements (Copied from BR Template)
Project Name: | Workforce Management
Project #: | <DSR019>
Date: | 2025-06-09
Req. No | Requirement Title | Category | Sub-Category | Requirement Description | MoSCoW Rating (use drop down values) | Scope Alignment | Domain (use drop down values) | Status | ATCO Comments | Approved by (Named individual) | Date (Approved)
BR-001 | View current training compliance by department, team, and supervisor | Data Access | Real-time Availability | Enable real-time access to training and competency data to support operational decisions | Must have | N/A | Data Analytics | N/A | N/A | N/A | N/A
BR-002 | Display upcoming expirations with countdown logic (120/90/60/30/7) | Reporting | Visualization | Develop a user-friendly dashboard that consolidates training data from Cornerstone, Oracle HCM, and My Time & Attendance, with countdown logic (120/90/60/30/7 days) for upcoming expirations. | Must have | N/A | Data Analytics | N/A | N/A | N/A | N/A
BR-003 | Filter reports by org unit, location, course, supervisor, and employee | Compliance | Audit Readiness | Automate reporting for AUC compliance, COR audits, and other regulatory needs. | Must have | N/A | Data Analytics | N/A | N/A | N/A | N/A
BR-004 | Compare training completion rates across departments and time periods | Reporting | Trend Analysis | Track historical trends in training completion to support planning and compliance. | Must have | N/A | Data Analytics | N/A | N/A | N/A | N/A
BR-005 | Summarize training costs per department and per employee | Cost Management | ROI & Budgeting | Provide financial insights into training investments and cost per learner. | Must have | N/A | Data Analytics | N/A | N/A | N/A | N/A
BR-006 | Highlight overdue/expired and non-compliant training items | Compliance | Exception Reporting | Automatically flag non-compliant users and departments for action. | Must have | N/A | Data Analytics | N/A | N/A | N/A | N/A
BR-007 | Provide role-based dashboard views | User Experience | Personalization | Enable tailored dashboard views for executives, managers, and schedulers. Currently, the Electric and Gas dashboards include two sections each (Training Leader and Competency Training), with 10–12 total pages per business unit. The target state is a consolidated Power BI dashboard with approximately 8–12 views, supporting streamlined navigation, reduced redundancy, and intuitive drill-downs by role and business unit. | Must have | N/A | Data Analytics | N/A | N/A | N/A | N/A
BR-008 | Enable download/export of compliance summaries | Reporting | Distribution | Allow users to export reports for offline use and external sharing. | Must have | N/A | Data Analytics | N/A | N/A | N/A | N/A
BR-009 | Incorporate visual indicators (e.g. red/yellow/green) for compliance levels | Reporting | Visualization | Provide at-a-glance indicators of training status across the organization. | Must have | N/A | Data Analytics | N/A | N/A | N/A | N/A
BR-010 | View training status for contractor vs employee populations | Data Access | Segmentation | Enable comparison of compliance by employee type for workforce planning. | Must have | N/A | Data Analytics | N/A | N/A | N/A | N/A
BR-011 | Identify training gaps by job role and business unit | Analytics | Gap Analysis | Highlight required training that has not yet been completed for critical roles. | Must have | N/A | Data Analytics | N/A | N/A | N/A | N/A
BR-012 | Enable filtering by job group, tenure, and location | User Experience | Search & Filter | Provide flexible filtering options to narrow report scope. | Must have | N/A | Data Analytics | N/A | N/A | N/A | N/A
BR-013 | Include historical training completions in compliance dashboards | Data Access | Historical Records | Display at least two years of training history alongside current status to support long-term trend analysis, audits, and compliance reviews. | Must have | N/A | Data Analytics | N/A | N/A | N/A | N/A
BR-014 | Enable access to dashboards from desktop and mobile devices | User Experience | Accessibility | Ensure dashboards are responsive and accessible from various devices. | Must have | N/A | Data Analytics | N/A | N/A | N/A | N/A
BR-015 | Allow tracking of certification renewal windows | Compliance | Renewal Monitoring | Track when re-certifications are due and alert supervisors/leaders accordingly. | Must have | N/A | Data Analytics | N/A | N/A | N/A | N/A
BR-016 | Track course demand to support resource planning | Analytics | Demand Forecasting | Analyze enrollment trends and historical completions to support demand forecasting, resource allocation, and potential ML-based optimization in future phases. | Should have | N/A | Data Analytics | N/A | N/A | N/A | N/A

## Non-Functional Requirements
IT Project Requirements Template
Non Functional Requirements
Project Name: | Workforce Management
Project #: | <DSR019>
Date: | 2025-06-09
Req. No | Requirement Title | Category | Requirement Description | MoSCoW Rating (use drop down values) | Req Category | Domain (use drop down values) | Status | ATCO Comments | Approved by (Named individual) | Date (Approved)
NFR-001 | Dashboard Usability | User Experience | The dashboard must be intuitive and easy to navigate for various user levels. | Must have | Usability | Data Analytics | N/A | N/A | N/A | N/A
NFR-002 | System Performance | Performance | Reports and dashboards should load within 3 seconds under normal conditions. | Should have | Performance | Data Analytics | N/A | N/A | N/A | N/A
NFR-003 | Data Accessibility and Availability | Data Quality | Ensure near real-time (daily or better) data availability across all integrated systems, with fallback logic if a source system is temporarily unavailable. | Must have | Availability | Data Analytics | N/A | N/A | N/A | N/A
NFR-004 | System Scalability | Architecture | The solution must be scalable to accommodate additional business units, data sources, and users without major rework. | Should have | Scalability | Data Analytics | N/A | N/A | N/A | N/A
NFR-005 | Secutiry and Row-level Access | Security | The dashboard must implement both role-based and row-level security, ensuring users can only view data appropriate to their role, department, or scope of responsibility. | Must have | Security | Data Analytics | N/A | N/A | N/A | N/A
NFR-006 | Auditability and Compliance Logging | Compliance | The system must maintain logs of data access and modifications to support AUC compliance and internal audit readiness | Should have | Auditability | Data Analytics | N/A | N/A | N/A | N/A
NFR-007 | Cross-Platform Compatibility | Usability | Dashboards and reports must be accessible on both desktop and mobile devices used by field staff and leadership. | Could have | Accessibility | Data Analytics | N/A | N/A | N/A | N/A
NFR-008 | Daily Data Refresh | Performance | Dashboards must be refreshed at least daily to ensure timely access to training and competency data, with a visible "Last Refreshed" timestamp. | Must have | Timeliness | Data Analytics | N/A | N/A | N/A | N/A
NFR-009 | Disaster Recovery and Data Backup | Security | Regular backups and recovery procedures must be in place to prevent data loss and ensure business continuity. | Should have | Reliability | Data Analytics | N/A | N/A | N/A | N/A
NFR-010 | Maintenance and Documentation | Supportability | All pipelines, transformation rules, and dashboard logic must be well-documented for seamless transition to internal teams. | Must have | Maintainability | Data Analytics | N/A | N/A | N/A | N/A
NFR-011 | Train-the-Trainer Readiness | Supportability | Provide structured documentation and support for ATCO's internal train-the-trainer model, including user guides and FAQs. | Must have | Maintainability | Data Analytics | N/A | N/A | N/A | N/A
NFR-012 | Dashboard Consolidation & Layout Optimization | Usability | The solution should consolidate existing Electric and Gas dashboards (~10–12 pages each) into a single, streamlined interface with ~8–12 core views, improving clarity and reducing page redundancy. Design should prioritize logical grouping of metrics and minimize page switching. | Should have | Usability | Data Analytics | N/A | N/A | N/A | N/A

## Technical Requirements NM (hidden)
IT Project Requirements Template
Technical Requirements
Project Name: | Payroll Optimization - Upgrade from Pay @ Work to WFN
Project #: | 1106804
Date: | 2025-02-20
Req. No | Requirement Title | Category | Requirement Description | MoSCoW Rating (use drop down values) | Req Category | Group | Status | ATCO Comments | Approved by (Named individual) | Date (Approved)
| Integration Error Handling | Integrations | Any error encountered during one of the ADP integration processes must be output to xxxxx |  | Integration errors | IT - Integration Team |  | Related to BR-023 OIC should be able to provide failure notifications
| Integration Error Handling | Integrations | Any error encountered during one of the ADP integration imports must be provided to ATCO via xxxx |  | Integration errors | ADP Team |  | Related to BR-025 Need to determine what this looks like
| Integration Encryption | Integrations | All outbound integrations must use PGP encryption |  | Data encryption | IT - Vendor
| Integration Encryption | Integrations | PER-176 and PER-176 must be provided to ATCO using xxxxx encryption |  | Data encryption | ADP Team
| Integration Delivery - Outbound | Integrations | All outbound integrations must be sent to ADP using OMFT | Must have | Integration delivery | IT - Vendor
| Integration Delivery - Outbound | Integrations | Integrations must scheduled with the following frequencies: ◦ Demo file daily ◦ Banking file daily ◦ Recurring pay daily ◦ Non-recurring pay bi-weekly/monthly as applicable (need to confirm as payroll still has this as a daily in their requirements) | Must have | HCM integration frequency | IT - Integration Team |  | Related to BR-019
| Integration Delivery - Outbound | Integrations | Integrations must scheduled with the following frequencies: ◦ Non-recurring pay bi-weekly/monthly as applicable | Must have | UKG integration frequency | IT - Integration Team |  | Related to BR-019, BR-029
| Integration Delivery - Inbound | Integrations | PER-173 and PER-176 must be provided to ATCO using SFTP | Must have | Integration delivery | ADP Team
| Effective dated data extract | Integrations | Oracle HCM records extracted for integrations must use the current effective dated record less than or equal to the date that the integration is run | Must have | HCM Integration data - Demo file | IT - Vendor |  | Related to BR-008, BR-009, BR-010
| Effective dated data extract | Integrations | Oracle HCM earnings and deductions extracted for the recurring pay integration must be active and/or ending during the pay period for which the file is being created (need to detail out how this will work from a parameter perspective if this is daily) | Must have | HCM Integration data | IT - Vendor |  | Related to BR-011, BR-012, BR-019
| Data for terminated employees | Integrations | Data for terminated employees must be included on all outbound integration files for 120 days from the date of termination and then drop off the file after 120 days | Should have | HCM Integration data | IT - Vendor |  | Related to BR-022
| Data transformation for WFN format | Integrations | To ensure connection with ADP's data requirements, data transformation needs to occur in a scalable format such as user-defined tables. All data transformation solutions must be scalable and accessable from the HRIS team. Data transofrmations need to occur for: ◦Payroll Name to ADP 3-digit Company Code ◦Oracle HCM employee status to WFN status | Must have | HCM Integration data | IT - HRIS
| Data output for WFN format | Integrations | The solution must include outbound integrations from Oracle to ADP that meet the WFN data format for each file type as provided as outlined in the solution design ◦ Employee demographic data file ◦ Employee banking information ◦ Employee recurring pay elements ◦ Employee non-recurring pay elements | Must have | HCM Integration data | IT - Vendor |  | Related to BR-019
| Data output for WFN format | Integrations | The solution must include outbound integrations from UKG to ADP that meet the WFN data format for each file type as provided as outlined in the solution design ◦ Employee timecard data and vacation banks | Must have | UKG Integration data | IT - Vendor
| Dental status extract | Integrations | The dental codes must be generated through logic into the demographic file using data from the employee benefit program and benefit eligability. The solution must be scalable for logic changes as new benefit programs are introduced and eligability changes. | Should have | HCM Integration data - Demo file | IT - Vendor |  | Related to BR-016 Waiting on ADP to provide field in demographic file template
| Removal of hard-coding for executive identification | Integrations | Hard-coding should be removed as much as possible from all integrations that are segregating data between executive and non-executive | Should have | HCM Integration data - Demo file | IT - Vendor |  | Related to BR-017
| International employee data | Integrations | International employees to be included in all payroll integration files as applicable | Should have | HCM Integration data | IT - Vendor |  | Related to BR-033
| GLI inbound (PER-173) | Integrations | ADP must provision GLI files for all payrolls for inclusion in the SFTP GLI file processing | Must have | Inbound Integration | ADP Team |  | Related to BR-018 Currently the monthly file is provisioned manually outside of the SFTP process.
| GLI inbound (PER-173) | Integrations | The GLI inbound integration must be modified to manage new ADP data (Company Codes) and to intake a monthly file that will manage cost reallocation transformation | Must have | Inbound Integration | IT - Vendor |  | Related to BR-018 Currently the monthly file is provisioned manually outside of the SFTP process.
| Isolated time record push from UKG | Integrations | Payroll has requested the ability to select individual pay data records from ADP and submit them to ADP for off-cycle processing | Could have | UKG Integration data | IT - Vendor |  | Related to BR-028 (recent ask by Trish) Kristine investigating if/how this could be accommodated in UKG **Pending confirmation from ADP if they can actually accept off-cycle paydata files
| UKG Configuration | Integrations | Daily hours breakdown must be sent directly from UKG to ADP on a bi-weekly basis. This would require reates to be maintained in UKG. | Must have | UKG Configuration | IT-HRIS |  | BR-029, need to confirm if ADP can intake daily breakdown
| HCM Configuration | HCM Data | Oracle HCM and Payroll must have all elements that are discontinued as end dated and all mapping of discontinued elements must be unmapped | Should have | HCM Configuration | IT - HRIS |  | Related to BR-035
| UKG Configuration | UKG Data | UKG must have all paycodes that are discontinued as end dated and all mapping of discontinued elements must be unmapped | Should have | UKG Configuration | IT - HRIS |  | Related to BR-035
| HCM Configuration | HCM Data | Elements in Oracle must but be automatically end dated for employees who are terminating for all earning and deductions | Could have | HCM Configuration | IT - HRIS |  | Related to BR-012 Will need to investigate if this is possible
| HCM Configuration | HCM Data | To facilitate the monthly GLI intake a method of storing cost splits for executive cost reallocations is required iacle HCM. | Should have | HCM Configuration | IT - HRIS
| HCM Configuration | HCM Data | Elements in Oracle must but be automatically end dated for employees who have salary continuance for specific earnings and deduction codes related to benefits, union dues, social, charity, premium pay and allowances |  |  |  |  | Related to BR-012 Will need to investigate if this is possible
| HCM Configuration | HCM Data | Elements in Oracle must but be automatically end dated for employees who are on a leave of absence for all earning codes |  |  |  |  | Related to BR-012 Will need to investigate if this is possible
| HCM Configuration | HCM Data | Elements in Oracle must but be automatically end dated for employees who are on a leave of absence for all earning codes with the exception of STD Codes
| HCM Configuration | HCM Data | For all elements that are automatically end dated, there must be an audit report to show what was end dated within the pay period for validation
| HCM Configuration | HCM Data | HR Help Desk Service request forms must be updated to show Service Requests related to board of directors to be able to easily identify board of director pay impacting requests
| Backdated Changes | Integrations | The Demographic file must pick up backdated transactions that are new for a period of xx |  |  |  |  | Not really an issue with a daily file as the data will always be greatest effective date less than or equal to sysdate so if a back dated change becomes the active record it will be picked up
| HCM Configuration | HCM Data | Oracle must calculate the pension contributions based on the 4% employee and 6% employer match against the salary and complete the prortation based on hire date and eligability Update | Won't (Would Like) |  |  |  | This is not feasible as pensionable earnings are not configured in HCM. Also some pensionable pay items exist in UKG which would require doing additional calculations and submission in the UKG integration. What CAN be sent is the percentage that should be used in the calculation based on the employee's pension enrollment data.
| Pension Logic | Integrations | Pension Contribution calculations must be sent on the pay data files | Won't (Would Like) |  |  |  | This is not feasible as pensionable earnings are not configured in HCM. Also some pensionable pay items exist in UKG which would require doing additional calculations and submission in the UKG integration. What CAN be sent is the percentage that should be used in the calculation based on the employee's pension enrollment data.
| Data output for WFN format | Integrations | The following outbound integrations are required and must meet the WFN data format for each file type as provided during solution design: ◦ Employee timecard data and vacation banks | Must have | UKG Integration data | IT - Vendor
| Removal of hard-coding for executive identification | Integrations | Hard-coding should be removed as much as possible from all integrations that are segregating data between executive and non-executive | Should have | HCM Integration data - Demo file | IT - Vendor |  | Related to BR-017
| International employee data | Integrations | International employees to be included in all payroll integration files as applicable | Should have | HCM Integration data | IT - Vendor |  | Related to BR-033
| GLI inbound (PER-173) | Integrations | ADP must provision GLI files for all payrolls for inclusion in the SFTP GLI file processing | Must have | Inbound Integration | ADP Team |  | Related to BR-018 Currently the monthly file is provisioned manually outside of the SFTP process.
| GLI inbound (PER-173) | Integrations | The GLI inbound integration must be modified to manage new ADP data (Company Codes) and to intake a monthly file that will manage cost reallocation transformation | Must have | Inbound Integration | IT - Vendor |  | Related to BR-018 Currently the monthly file is provisioned manually outside of the SFTP process.
| Isolated time record push from UKG | Integrations | Payroll has requested the ability to select individual pay data records from ADP and submit them to ADP for off-cycle processing | Could have | UKG Integration data | IT - Vendor |  | Related to BR-028 (recent ask by Trish) Kristine investigating if/how this could be accommodated in UKG **Pending confirmation from ADP if they can actually accept off-cycle paydata files
| HCM Configuration | HCM Data | Clean-up exercise to end date and unmap paycodes that will be discontinued | Should have | HCM Configuration | IT - HRIS |  | Related to BR-035
| UKG Configuration | UKG Data | Clean-up exercise to end date and unmap paycodes that will be discontinued | Should have | UKG Configuration | IT - HRIS |  | Related to BR-035
| HCM Configuration | HCM Data | Payroll has requested automation of Payroll Elements to all be end dated based on status changes (eg Termination, Unpauid Leave etc…) as a way to minimimze manual entry by the ERC/processing team | Could have | HCM Configuration | IT - HRIS |  | Related to BR-012 Will need to investigate if this is possible
| HCM Configuration | HCM Data | To facilitate the monthly GLI intake a method of storing cost splits for executive cost reallocations is required iacle HCM. | Should have | HCM Configuration | IT - HRIS
Note on D7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This needs to be completed
Note on D12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This does not align with the requirement for non-recurring pay in BR-019
Note on D15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Can we call out that this is the demographic file
Note on D25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I thought we took out the cost reallocation? Is this still a requirement? Reply: We are taking the approach to include all requirements but mark the out of scope ones in the MoSCoW rating as W for ‘Won’t but would like’ . Then we have a way of capturing all of the potential Phase 2 items in this document rather than maintaining a separate one. (trying to avoid the multiple documents scenario)
Note on D26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to be re-written as a requirement(s) once we get confirmation from ADP

## Technical Requirements
IT Project Requirements Template
Technical Requirements
Project Name: | Workforce Management
Project #: | <DSR019>
Date: | 2025-06-09
Req. No | Requirement Title | Category | Requirement Description | MoSCoW Rating (use drop down values) | Req Category | Domain (use drop down values) | Status | Dependent Tech Req # | Business Requirement # | Link to BR | ATCO Comments | Approved by (Named individual) | Date (Approved)
TR-001 | Data Integration from Core Systems | Data Integration | Ingest and integrate data from Cornerstone, Oracle, and My Time & Attendance | Must have | Data Pipeline | Data Analytics | N/A | N/A | BR-002 | TBD | N/A | N/A | N/A
TR-002 | Role-Based Access Control | Security | Implement access control based on user role and row-level security filters (e.g., business unit, supervisor, individual employee) to ensure appropriate data visibility and drill-down access across different user types. | Should have | Security | Data Analytics | N/A | N/A | BR-002 | TBD | N/A | N/A | N/A
TR-003 | Data Validation Rules | Data Quality | Implement transformation and validation logic to ensure consistency across systems and metrics | Must have | Data Pipeline | Data Analytics | N/A | N/A | BR-001, BR-002 | TBD | N/A | N/A | N/A
TR-004 | Metadata and Audit Logs | Data Governance | Track lineage, timestamps, and changes for ELT processes to support auditability and troubleshooting. | Should have | Data Governance | Data Analytics | N/A | N/A | BR-001, BR-003 | TBD | N/A | N/A | N/A
TR-005 | Alert Configuration Engine | Monitoring | Configure thresholds and alerts for expiring training, data pipeline failures, and performance degradation. | Must have | Monitoring | Data Analytics | N/A | N/A | BR-002 | TBD | N/A | N/A | N/A
TR-006 | Power BI Integration and Optimization | Visualization | Integrate Power BI into ATCO's environment and optimize for responsive, multi-level dashboard rendering. | Must have | Visualization | Data Analytics | N/A | N/A | BR-002, BR-003 | TBD | N/A | N/A | N/A
TR-007 | Knowledge Transfer and Documentation | Delivery | Document pipeline design, metrics logic, and dashboard navigation to support handoff and internal ownership. | Must have | Supportability | Data Analytics | N/A | N/A | BR-003 | TBD | N/A | N/A | N/A
TR_008 | Historical Data Support | Data Modeling | Ensure historical training records are ingested, mapped, and retained in the data model to support trend analysis, auditability, and comparisons over time. | Must have | Data Modeling | Data Analytics | N/A | N/A | BR-013 | TBD | N/A | N/A | N/A

## Use Cases (hidden)
Use-case # | Description | Use Case Name (Use an active verb phrase that describes a particular task). | Subject Area (Use role or other grouping mechanism that can be used to group use cases). | Business event (is a trigger that stimulates activity within the business. Many business events occur at the interface point between the business and one of the external entities with which it interacts. Business events must be observable). | Actors (The actor that initiates this use case and all users who participate in this use case). | Use case overview (A description of the overall scope and content of the use case). | Preconditions Constraints (These must be met for the use case to be taken by the solution developer and used to create a workflow. This might include a required sequencing of use cases. For example, one or more other use cases might need to be performed successfully for this use case to begin). | Termination outcome (A list of the successful and unsuccessful ways this use case might end. What are the possible ending results?) | Condition affecting termination outcome (A list of the conditions under which the corresponding termination outcome occurs). | Use case description (A brief description of events for the most likely termination outcome. List the actions the actor does and how the system responds). | Use case associations (A list of other use cases that are associated with this use) case. | Traceability (to a list of other related Functional or NonFunctional requirements, or documents, or models, and products that are associated with this use case.) | Input summary (A brief summary that lists the data input by the actor). | Output summary (A brief summary that lists the data output by the system). | Usability index (A number based on how this use case ranked in terms of satisfaction, importance, and frequency). | Use case notes (Information that is not directly part of this use case but that the solution developer needs to be aware of while working on the workflow).
UC0001 | Multiple PMs | [10 empty] | F-0001
UC0002
UC0003
UC0004
UC0005
UC0006
UC0007
UC0008
UC0009
UC0010
UC0011
UC0012
UC0013
UC0014
UC0015
UC0016
UC0017
UC0018
UC0019
UC0020
UC0021
UC0022
UC0023
UC0024
UC0025
UC0026
UC0027
UC0028
UC0029
UC0030
UC0031
UC0032
UC0033
UC0034
UC0035
UC0036
UC0037
UC0038
UC0039
UC0040
UC0041
UC0042
UC0043
UC0044
UC0045
UC0046

## Legends and Lookups
Domains | Functional Category Legend | Non-Functional Category Legend | UAT Pass/Fail | MuSCoW Requirements Ranking
AI | Reporting | Security | Pass | MU | Must have | Requirements labeled as MUST are critical to the current delivery timebox in order for it to be a success. If even one MUST requirement is not included, the project delivery should be considered a failure (note: requirements can be downgraded from MUST, by agreement with all relevant stakeholders; for example, when new requirements are deemed more important). MUST can also be considered a acronym for the Minimum Usable Subset.
BPSS | Interfaces | Availability | Fail | S | Should have | Requirements labeled as SHOULD are important but not necessary for delivery in the current delivery timebox. While SHOULD requirements can be as important as MUST, they are often not as time-critical or there may be another way to satisfy the requirement, so that it can be held back until a future delivery timebox.
CCS | Conversions | Usability |  | CO | Could have | Requirements labeled as COULD are desirable but not necessary, and could improve user experience or customer satisfaction for little development cost. These will typically be included if time and resources permit.
CIS | Enhancements | System Help |  | W | Won't (Would Like) | Requirements labeled as WON'T have been agreed by stakeholders as the least-critical, lowest-payback items, or not appropriate at that time. As a result, WON'T requirements are not planned into the schedule for the delivery timebox. WON'T requirements are either dropped or reconsidered for inclusion in later timeboxes. (Note: occasionally the term Would like is substituted, to give a clearer understanding of this choice)
Data Analytics | Forms | Performance |  | Q | Question For Vendor
GEA | Audit & Controls | Scalability
Gtech | Workflow | Data Conversion and Migration
Integration | Business logic | Data
Maximo | User interface | OCM
OFS | Regulatory | Decommissioning
| Health & Safety | Service Level Agreements
Transition to Operations
Disaster Recovery
Employee Experience
Integration